## Sheet1
Number | Task | Priority | Notes | LM Notes | KEY
7 | Total score should be the average of all surveys – not the total. So if we have two surveys scoring 5,6,7 and 10,10,10, the total score should be the average of 18 and 30 = 24. At the moment it is showing 48. | DONE |  |  | Done
18 | Detail reports missing data. I ran a report for the current month but it only showed one call when many more test calls have been made | DONE |  |  | Not sure if complete
3 | Error handling – Php error needs to be replaced with something more functional – for example “this record doesn’t exist” “please contact the system administrator” | 2 | Not sure? | Not mentioned before | Partially complete
4 | Initial preview of reports different to final output, needs to be the same. | 2 | Not done | Not mentioned before but is being looked into | Not done
9 | Don’t like the new wordcloud design. Can we discuss. Like that it is multi-coloured but don’t like the font. | DONE
10 | Position of dashboard data – need to have the titles higher and the data in the centre of the box – see shoutdemo wordcloud for good example – using IE | DONE
13 | Wallboard screens need tidying up – for all types, there should just be a heading, tickertape and then the data – as big as possible. Let me know if you need screenshots | 2 | data report showing all heading information - wordcloud not in middle of screen and sized too big so that won't fit on one screen. | Will be fixed
15 | Data reports showing as detail reports. Data reports should be summarised reports that show numerical information over time. For example, if there were 76 surveys completed in a day, we would have a detail report showing every call – but the data report would show a summary. Note: in data reports, detail components need to be shown as a count – eg Transcriptions will show the number of calls that have a transcription. Data reports should also allow drill down to the detail report that makes up the data report. | 2 | Need surveys count column. Also the intervals box disappears when data type slected - this shouldn't happen as data reports need to be subtotalled by interval
16 | Missing some key data in reports. They are Maximum Scores (where MaxTotal = ScoreTotal) and Incompletes (where at least one question is not answered by the customer | 2 | Not done | Not mentioned before
20 | Dates selected not showing in the title of the report – eg 1st August – 14th October or Last Month | 2 | Not sure?
23 | Need reports to be defined by question score. So if we have Q1 between 1 and 5, I want to be able to show the number of surveys that have scored each of the questions. One way of doing this will be to add a question box into the Reference field as well – so that if the customer chooses reference Question, and then Numerical Question 1, the system will show the totals for each score | 2 | Not done | Working on, as it requires quite a lot of redesign to work.
2 | When setting up a user, the email doesn’t let the person know what their username is and it should as it will save time and also save them from having to chase us or their admin for the username. | DONE
6 | Y-Axis midpoint not moving the Y axis | 3 | Not done | Should be done, as it's set up for the Y-Axis on the dashboard and fullscreen. Preview might be an issue, will look into
8 | We get a warning box on the reports filter asking that tags has to be selected in the data selection area – this shouldn’t be so. We should be able to filter by tag without showing it. | 3 | Not sure? | Not mentioned before
11 | The email functionality is not working and also there should be a repetitive time to send the emails – as per the original spec. Can we add this at some stage please? | 3 | Not done
17 | Show the data reports on wallboards as tables | 3 | Not sure? | It is mentioned there as tables now, but as mentioned above, it is not having wanted buildup
24 | Allowing data and detail reports to be sorted by clicking on columns | DONE
12 | Can FTP be reserved for only detail reports please? | 4 | Not done | Not mentioned before
14 | Can we change the tickertape to move along the field and disappear off of the end – rather than the revealing style we have now? | DONE
19 | Custom Dates not working. I ran a report for August to current date and nothing was shown | 4 | Not working for detail - not sure if working elsewhere
22 | When going backwards from the Report Preview page, the filter warning box appears. It shouldn’t appear when going back. | DONE | Done I think.
21 | The display box should be defaulted to on-screen. It just shows as ‘select’ | DONE
1 | Users - Delete a user option now present but you need to add a prompt to acknowledge the user has been deleted, similar to the prompt that appears when adding/removing a report from the dashboard. | DONE
5 | Missed question assigning as zero when it should be null. | DONE